## Sheet1
Yearly plan
Year | Major Objective
2025 | Migrate on-premises workloads to the cloud
Q1 | Assess current infrastrusture and plan migration
Q2 | Set up cloud envronment and configuration
Q3 | Migrate application and check performance
Q4 | Testing and Monitoring
Week | component | Deliverable | Estimated Time(Hours) | Proposed difficulty (1-5)
2025-10-01 | Infrastructure Assesment | Audit current workloads and dependencies | 10 | 3
2025-10-08 | Infrastructure Assesment | Identify applications for migration | 8 | 2
2025-10-15 | Cloud Setup | Deploy cloud resources (VMs, Storage, Databases) | 12 | 4
2025-10-22 | Cloud Security | Implement IAM roles and policies | 10 | 4
2025-10-29 | Cloud Networking | Set up VPN and VPC configurations | 10 | 4
2025-11-05 | Cloud Migration | Test migration process on non-critical apps | 15 | 5
2025-11-12 | Cloud Migration | Migrate critical applications | 20 | 5
2025-11-19 | Performance Optimization | Optimize cloud workloads and costs | 8 | 3
2025-11-26 | Post-Migration Testing | Conduct security & performance tests | 10 | 3
2025-12-03 | Monitoring & Logging | Set up cloud monitoring tools | 7 | 2
2025-12-10 | Documentation | Train staff on cloud best practices | 6 | 2
2025-12-17 | Documentation | Train staff on cloud best practices | 6 | 2
| Goals | Goals
Successful migration to the cloud
Enhancing security